## Sprint 0
PRE-SPRINT PLANNING (SPRINT 0)
Product Vision | Build an AI-powered smart IT support ticket resolution system that retrieves relevant knowledge, suggests high-confidence resolutions, tracks knowledge gaps, and provides an easy-to-use web interface for users and admins.
Definition of Done (DoD) | A user story is complete only when code is implemented, reviewed, tested, integrated, documented, and ready for demonstration without critical defects.
Sprint 0 Deliverables
Item | Details | Status
Product Vision | Project objective and expected outcome documented | Done
Initial Product Backlog | Features and sprint goals drafted for 9 sprints | Done
Definition of Done | Completion criteria agreed for all user stories | Done
Architecture Direction | RAG + LLM + Streamlit + SQLite solution baseline defined | Done

## Overview
AGILE DOCUMENT OVERVIEW
Project Name | AI Powered Smart Support & Ticket Resolution
Developer | S Pujith Reddy
Total Planned Sprints | 9
Current Documentation Includes | Sprint 0, Product Backlog, Sprint Backlog, Stand Up Meeting, Sprint Review, Retrospection, Final Handover, Legend

## Product Backlog
SL | Sprint | Sprint Period | Sprint Goal | Tasks Planned | Tasks Completed | Deliverables | Status
1 | Sprint 1 | 18 Feb 2026 – 24 Feb 2026 | Requirement analysis and project planning | Requirement gathering, problem understanding, system scope definition, tech stack finalization | Requirements documented, architecture drafted | Requirement Specification, High-level Architecture | Completed
2 | Sprint 2 | 25 Feb 2026 – 03 Mar 2026 | Knowledge base design and data preparation | Knowledge base schema design, sample ticket & article collection, FAISS vector store setup | Data schema finalized, initial dataset prepared, FAISS index created | Structured knowledge base, sample data, faiss_index folder | Completed
3 | Sprint 3 | 04 Mar 2026 – 10 Mar 2026 | RAG engine & embedding pipeline | Build rag_engine.py with OllamaEmbeddings (tinyllama), document ingestion, chunk splitting | RAG engine implemented, ingest.py working, FAISS index populated | rag_engine.py, ingest.py, processed PDFs | Completed
4 | Sprint 4 | 11 Mar 2026 – 17 Mar 2026 | LLM engine & AI resolution generation | Build llm_engine.py with llama3.2:1b, prompt engineering, confidence scoring logic | LLM engine generating resolutions, confidence & status logic working | llm_engine.py with analyze_ticket(), confidence scoring | Completed
5 | Sprint 5 | 18 Mar 2026 – 24 Mar 2026 | Feature Expansion (Part 1) – AI smart resolution enhancements | AI chat-style resolution flow, response refinement, confidence score improvements, resolution explanation output, interaction log capture | AI-assisted resolution workflow enhanced, response traceability improved, interaction logging prepared | ai_interaction_logs, refined llm_engine.py, response explanation module | Completed
6 | Sprint 6 | 25 Mar 2026 – 31 Mar 2026 | Feature Expansion (Part 2) – secondary features & analytics | Knowledge gap analytics dashboard, admin ticket insights, file/document handling improvements, threshold tuning, reporting support | Secondary features integrated, admin insights improved, tuning support added | ticket_service.py, admin insights view, knowledge gap analytics summary | In Progress
7 | Sprint 7 | 01 Apr 2026 – 07 Apr 2026 | Streamlit UI – frontend development | Build app.py with login/signup page, New Incident tab, My History tab, admin view | Fully functional web UI, dark-mode CSS, session state management | app.py (Streamlit), custom CSS, run.py launcher | Planned
8 | Sprint 8 | 08 Apr 2026 – 14 Apr 2026 | Testing, optimization & documentation | End-to-end testing via test_backend.py, bug fixing, config.py env tuning, project docs | Stable system, all tests passing, documentation complete | test_backend.py results, project_modules_guide.md, final app | Planned
9 | Sprint 9 | 15 Apr 2026 – 21 Apr 2026 | Deployment, handover & final documentation | Production deployment setup, deployment guide, final handover document, maintenance guide, project demo preparation | App deployed, handover document ready, maintenance guide written | deployment_guide.md, handover_document.md, final demo recording | Planned

## Sprint Backlog
NOTE: Task sizing should be between 0.5 to 12 hours |  |  |  | Assignee: S Pujith Reddy
Story ID | Task ID | User Story / Task | Story Points | Assignee | Task Start Date | Task Completion Date | Activity | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
SPRINT 1 BACKLOG ¦ 18 Feb 2026 – 24 Feb 2026 ¦ Assignee: S Pujith Reddy
US-01 | T-01 | Gather functional requirements & define problem scope | 4 | S Pujith Reddy | 18 Feb 2026 | 18 Feb 2026 | Analysis | Completed | 0 | 4 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Define tech stack (Python, Ollama, FAISS, Streamlit, SQLite) | 2 | S Pujith Reddy | 18 Feb 2026 | 19 Feb 2026 | Planning | Completed | 0 | 0 | 2 | 0 | 0 | 0 | 0
US-01 | T-03 | Design high-level architecture diagram | 3 | S Pujith Reddy | 19 Feb 2026 | 20 Feb 2026 | Design | Completed | 0 | 0 | 3 | 0 | 0 | 0 | 0
US-01 | T-04 | Document requirement specification | 4 | S Pujith Reddy | 20 Feb 2026 | 21 Feb 2026 | Documentation | Completed | 0 | 0 | 0 | 4 | 0 | 0 | 0
US-01 | T-05 | Create project folder structure & initialize git | 2 | S Pujith Reddy | 21 Feb 2026 | 21 Feb 2026 | Setup | Completed | 0 | 0 | 0 | 0 | 2 | 0 | 0
SPRINT 2 BACKLOG ¦ 25 Feb 2026 – 03 Mar 2026 ¦ Assignee: S Pujith Reddy
US-02 | T-06 | Design SQLite schema for tickets, users, knowledge_gap_events | 3 | S Pujith Reddy | 25 Feb 2026 | 25 Feb 2026 | Design | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-07 | Collect sample IT support tickets & knowledge articles | 4 | S Pujith Reddy | 25 Feb 2026 | 26 Feb 2026 | Research | Completed | 0 | 4 | 0 | 0 | 0 | 0 | 0
US-02 | T-08 | Set up data/raw and data/processed directory structure | 2 | S Pujith Reddy | 26 Feb 2026 | 26 Feb 2026 | Setup | Completed | 0 | 2 | 0 | 0 | 0 | 0 | 0
US-02 | T-09 | Test PDF ingestion with sample documents | 3 | S Pujith Reddy | 27 Feb 2026 | 28 Feb 2026 | Testing | Completed | 0 | 0 | 3 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG ¦ 04 Mar 2026 – 10 Mar 2026 ¦ Assignee: S Pujith Reddy
US-03 | T-10 | Implement OllamaEmbeddings class (tinyllama model) | 4 | S Pujith Reddy | 04 Mar 2026 | 04 Mar 2026 | Development | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-11 | Build ingest_documents() with FAISS index creation | 5 | S Pujith Reddy | 05 Mar 2026 | 05 Mar 2026 | Development | Completed | 0 | 5 | 0 | 0 | 0 | 0 | 0
US-03 | T-12 | Implement get_relevant_context() with similarity scoring | 4 | S Pujith Reddy | 06 Mar 2026 | 06 Mar 2026 | Development | Completed | 0 | 0 | 4 | 0 | 0 | 0 | 0
US-03 | T-13 | Build ingest.py CLI with tqdm progress bars | 3 | S Pujith Reddy | 07 Mar 2026 | 07 Mar 2026 | Development | Completed | 0 | 0 | 0 | 3 | 0 | 0 | 0
US-03 | T-14 | Run ingest on IT-SOP and Network Config PDFs | 2 | S Pujith Reddy | 08 Mar 2026 | 08 Mar 2026 | Testing | Completed | 0 | 0 | 0 | 0 | 2 | 0 | 0
SPRINT 4 BACKLOG ¦ 11 Mar 2026 – 17 Mar 2026 ¦ Assignee: S Pujith Reddy
US-04 | T-15 | Implement analyze_ticket() with RAG context injection | 6 | S Pujith Reddy | 11 Mar 2026 | 12 Mar 2026 | Development | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-16 | Build confidence scoring logic (_calculate_confidence) | 4 | S Pujith Reddy | 12 Mar 2026 | 13 Mar 2026 | Development | Completed | 0 | 4 | 0 | 0 | 0 | 0 | 0
US-04 | T-17 | Implement resolution_status threshold (resolved/tentative) | 3 | S Pujith Reddy | 13 Mar 2026 | 14 Mar 2026 | Development | Completed | 0 | 0 | 3 | 0 | 0 | 0 | 0
US-04 | T-18 | Add model availability check & auto-pull logic | 2 | S Pujith Reddy | 15 Mar 2026 | 15 Mar 2026 | Development | Completed | 0 | 0 | 0 | 0 | 2 | 0 | 0
SPRINT 5 BACKLOG ¦ 18 Mar 2026 – 24 Mar 2026 ¦ Assignee: S Pujith Reddy
US-05 | T-19 | Implement AI chat-style response flow for ticket resolution | 5 | S Pujith Reddy | 18 Mar 2026 | 19 Mar 2026 | Development | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-20 | Improve confidence scoring and response explanation output | 4 | S Pujith Reddy | 19 Mar 2026 | 20 Mar 2026 | Development | Completed | 0 | 4 | 0 | 0 | 0 | 0 | 0
US-05 | T-21 | Add AI interaction log capture for audit and analysis | 3 | S Pujith Reddy | 20 Mar 2026 | 21 Mar 2026 | Development | Completed | 0 | 0 | 3 | 0 | 0 | 0 | 0
US-05 | T-22 | Test expanded AI resolution feature set and quality | 3 | S Pujith Reddy | 22 Mar 2026 | 22 Mar 2026 | Testing | Completed | 0 | 0 | 0 | 0 | 0 | 3 | 0
SPRINT 6 BACKLOG ¦ 25 Mar 2026 – 31 Mar 2026 ¦ Assignee: S Pujith Reddy
US-06 | T-23 | Build knowledge gap analytics and ticket insight service | 6 | S Pujith Reddy | 25 Mar 2026 | 26 Mar 2026 | Development | In Progress | 6 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-24 | Implement grouped admin insights for recurring issues | 5 | S Pujith Reddy | 26 Mar 2026 | 27 Mar 2026 | Development | In Progress | 0 | 5 | 0 | 0 | 0 | 0 | 0
US-06 | T-25 | Add document/file handling support for ticket context | 3 | S Pujith Reddy | 28 Mar 2026 | 29 Mar 2026 | Development | Planned | 0 | 0 | 0 | 3 | 0 | 0 | 0
US-06 | T-26 | Integrate reporting support and threshold tuning | 2 | S Pujith Reddy | 30 Mar 2026 | 31 Mar 2026 | Development | Planned | 0 | 0 | 0 | 0 | 0 | 2 | 0
SPRINT 7 BACKLOG ¦ 01 Apr 2026 – 07 Apr 2026 ¦ Assignee: S Pujith Reddy
US-07 | T-27 | Build Streamlit login/signup UI page | 5 | S Pujith Reddy | 01 Apr 2026 | 02 Apr 2026 | Development | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-28 | Build New Incident submission form & AI result display | 5 | S Pujith Reddy | 02 Apr 2026 | 03 Apr 2026 | Development | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-29 | Build My History tab with expandable tickets | 4 | S Pujith Reddy | 04 Apr 2026 | 05 Apr 2026 | Development | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-30 | Add dark-mode CSS styling (Inter font, blue #3b82f6) | 3 | S Pujith Reddy | 06 Apr 2026 | 06 Apr 2026 | Design | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 8 BACKLOG ¦ 08 Apr 2026 – 14 Apr 2026 ¦ Assignee: S Pujith Reddy
US-08 | T-31 | Run test_backend.py automated test suite | 4 | S Pujith Reddy | 08 Apr 2026 | 09 Apr 2026 | Testing | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-32 | Fix all bugs found during testing | 6 | S Pujith Reddy | 09 Apr 2026 | 11 Apr 2026 | Bug Fix | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-33 | Optimize LLM prompt for better resolution quality | 4 | S Pujith Reddy | 11 Apr 2026 | 12 Apr 2026 | Optimization | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-34 | Finalize project_modules_guide.md documentation | 4 | S Pujith Reddy | 13 Apr 2026 | 14 Apr 2026 | Documentation | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 9 BACKLOG ¦ 15 Apr 2026 – 21 Apr 2026 ¦ Assignee: S Pujith Reddy
US-09 | T-35 | Set up production environment & deploy app | 5 | S Pujith Reddy | 15 Apr 2026 | 16 Apr 2026 | Deployment | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-36 | Write deployment guide & configuration docs | 4 | S Pujith Reddy | 16 Apr 2026 | 17 Apr 2026 | Documentation | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-37 | Create final project handover document | 4 | S Pujith Reddy | 17 Apr 2026 | 18 Apr 2026 | Documentation | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-38 | Write maintenance guide & known issues log | 3 | S Pujith Reddy | 19 Apr 2026 | 20 Apr 2026 | Documentation | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-39 | Prepare project demo & final presentation | 3 | S Pujith Reddy | 20 Apr 2026 | 21 Apr 2026 | Presentation | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand Up Meeting
DAILY STAND-UP LOG ¦ Project: AI Smart Support & Ticket Resolution ¦ S Pujith Reddy
Sprint | Day / Date | What I Did Yesterday | What I'll Do Today | Impediments / Blockers
1 | 18 Feb 2026 | Project kickoff | Requirements gathering | None
1 | 19 Feb 2026 | Requirements gathered | Tech stack selection | None
1 | 20 Feb 2026 | Tech stack finalized | Architecture design | None
1 | 21 Feb 2026 | Architecture drafted | Requirement spec doc | None
1 | 22 Feb 2026 | Spec doc written | Folder setup & git init | None
2 | 25 Feb 2026 | Folder structure ready | DB schema design | None
2 | 26 Feb 2026 | DB schema designed | Sample data collection | None
2 | 27 Feb 2026 | Data collected | Test PDF ingestion | Ollama model slow on CPU
2 | 28 Feb 2026 | PDF ingestion tested | Finalize sprint 2 | None
3 | 04 Mar 2026 | Sprint 2 delivered | Implement OllamaEmbeddings | None
3 | 05 Mar 2026 | Embeddings working | Build ingest_documents() | FAISS install took extra time
3 | 06 Mar 2026 | Ingest working | Implement get_relevant_context() | None
3 | 07 Mar 2026 | Context retrieval working | Build ingest.py CLI | None
3 | 08 Mar 2026 | CLI script done | Run ingest on sample PDFs | None
4 | 11 Mar 2026 | RAG engine ready | Build analyze_ticket() | None
4 | 12 Mar 2026 | analyze_ticket() done | Confidence scoring | None
4 | 13 Mar 2026 | Confidence scoring done | Resolution status thresholds | None
4 | 15 Mar 2026 | LLM engine complete | Model pull logic | None
5 | 18 Mar 2026 | LLM engine ready | Build AI chat-style response flow | None
5 | 19 Mar 2026 | Chat-style flow done | Improve confidence scoring & explanations | None
5 | 20 Mar 2026 | Scoring update done | Add AI interaction logging | None
5 | 22 Mar 2026 | Interaction logging done | Test expanded AI features | None
6 | 25 Mar 2026 | Sprint 5 feature expansion ready | Build knowledge gap analytics | None
6 | 26 Mar 2026 | Analytics in progress | Implement grouped admin insights | None
6 | 27 Mar 2026 | Admin insights in progress | Continue recurring issue grouping | Complexity higher than estimated
6 | 28 Mar 2026 | Grouping logic done | Add document handling support | None
6 | 30 Mar 2026 | Document support added | Integrate reporting and threshold tuning | None
6 | 31 Mar 2026 | Reporting support done | Sprint 6 wrap-up & review | None
7 | 01 Apr 2026 | Sprint 6 delivered | Build Streamlit login/signup page | None
7 | 02 Apr 2026 | Login UI in progress | Build New Incident form & AI display | None
7 | 03 Apr 2026 | Incident form done | Build My History tab | None
7 | 04 Apr 2026 | History tab in progress | Continue My History tab | None
7 | 06 Apr 2026 | History tab done | Add dark-mode CSS styling | None
7 | 07 Apr 2026 | CSS styling done | Sprint 7 review & wrap-up | None
8 | 08 Apr 2026 | Sprint 7 delivered | Run test_backend.py test suite | None
8 | 09 Apr 2026 | Tests running | Fix bugs found during testing | Some edge-case failures in ticket resolution
8 | 11 Apr 2026 | Bugs fixed | Optimize LLM prompt quality | None
8 | 13 Apr 2026 | Prompt optimized | Finalize project_modules_guide.md | None
8 | 14 Apr 2026 | Docs complete | Sprint 8 final review | None
9 | 15 Apr 2026 | Sprint 8 delivered | Set up production environment | None
9 | 16 Apr 2026 | Production env ready | Write deployment guide | None
9 | 17 Apr 2026 | Deployment guide done | Create handover document | None
9 | 19 Apr 2026 | Handover doc in progress | Write maintenance guide | None
9 | 20 Apr 2026 | Maintenance guide done | Prepare project demo | None
9 | 21 Apr 2026 | Demo prepared | Final submission & project closure | None

## Sprint Review
SL # | Sprint # | Sprint Dates | What was demonstrated | Stakeholder Feedback | Approved by
1 | Sprint 1 | 18 Feb 2026 – 24 Feb 2026 | Requirement specification, scope definition, architecture draft | Approved to proceed with technical implementation baseline | Project Guide / Faculty
2 | Sprint 2 | 25 Feb 2026 – 03 Mar 2026 | Knowledge base schema, sample ticket dataset, FAISS setup | Requested stronger validation of ingestion pipeline early | Project Guide / Faculty
3 | Sprint 3 | 04 Mar 2026 – 10 Mar 2026 | RAG engine, document ingestion flow, context retrieval | Good progress; add more logging for debugging and traceability | Project Guide / Faculty
4 | Sprint 4 | 11 Mar 2026 – 17 Mar 2026 | LLM ticket analysis, confidence scoring, resolution status logic | Suggested externalizing thresholds to config for flexibility | Project Guide / Faculty
5 | Sprint 5 | 18 Mar 2026 – 24 Mar 2026 | AI chat-style resolution flow, improved confidence scoring, explanation output, interaction logging | Feature expansion accepted; continue with analytics and secondary capabilities | Project Guide / Faculty
6 | Sprint 6 | 25 Mar 2026 – 31 Mar 2026 | Knowledge gap analytics, grouped recurring issue insights, document support, tuning controls | Good secondary feature coverage; improve reporting readability for admin users | Project Guide / Faculty
7 | Sprint 7 | 01 Apr 2026 – 07 Apr 2026 | Streamlit login UI, incident form, ticket history, dark-mode styling | Requested polished error states and better responsive layout | Project Guide / Faculty
8 | Sprint 8 | 08 Apr 2026 – 14 Apr 2026 | Backend tests, bug fixes, prompt tuning, final technical docs | Proceed after UAT sign-off and benchmark documentation | Project Guide / Faculty
9 | Sprint 9 | 15 Apr 2026 – 21 Apr 2026 | Production deployment, handover pack, maintenance guide, final demo | Accepted for project closure after final deployment verification | Project Guide / Faculty

## Retrospection
SPRINT RETROSPECTION ¦ Developer: S Pujith Reddy ¦ AI Smart Support & Ticket Resolution
SL # | Sprint # | Sprint Start Date | Sprint End Date | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 18 Feb 2026 | 24 Feb 2026 | Create detailed sub-tasks for each requirement item | Spending too much time on vague goal definitions | Systematic requirement documentation approach | Added task breakdown template for next sprint
2 | Sprint 2 | 25 Feb 2026 | 03 Mar 2026 | Test embeddings earlier in the sprint cycle | Waiting until end of sprint to validate ingestion pipeline | Good schema-first design approach | Scheduled embedding tests on Day 2 of each sprint
3 | Sprint 3 | 04 Mar 2026 | 10 Mar 2026 | Add logging to all RAG operations for debuggability | Running full ingestion without checking sample output first | Incremental development (embed → index → query) | Added logging.INFO calls throughout rag_engine.py
4 | Sprint 4 | 11 Mar 2026 | 17 Mar 2026 | Unit-test each LLM prompt variant before finalizing | Hardcoding confidence thresholds — use config.py instead | Modular function design (_calculate_confidence, _suggest_kb_filename) | Moved all thresholds to .env via config.get_float_env()
5 | Sprint 5 | 18 Mar 2026 | 24 Mar 2026 | Prototype major AI-facing features as user flows before implementation | Treating AI output quality checks as only end-stage validation | Iterative prompt and scoring refinement | Added feature-level testing for explanations and confidence output
6 | Sprint 6 | 25 Mar 2026 | 31 Mar 2026 | Bundle secondary features into smaller measurable increments | Combining analytics, reporting, and file support too late in one stream | Using ticket patterns to guide admin feature design | Split secondary feature work into analytics, file support, and reporting checkpoints
7 | Sprint 7 | 01 Apr 2026 | 07 Apr 2026 | Prototype UI sketches before coding | Jumping straight to code without UI wireframe planning | Iterative UI development | Created quick Figma sketch before Sprint 7 coding began
8 | Sprint 8 | 08 Apr 2026 | 14 Apr 2026 | Add CI test run before final submission | Leaving full test coverage to the last sprint only | Comprehensive documentation | Set up CI step to auto-run tests on each commit
9 | Sprint 9 | 15 Apr 2026 | 21 Apr 2026 | Record a walkthrough video during deployment for future reference | Leaving handover documentation until the final day | Thorough documentation culture established across all sprints | Scheduled handover doc writing from Day 2 of Sprint 9

## Legend
COLOUR LEGEND
| Green | Completed – Sprint/task fully done
| Yellow | In Progress – Currently active
| Grey | Planned – Upcoming, not started
| Blue | Alternating row highlight
| Salmon | Notes / Important information
Developer: S Pujith Reddy ¦ Project: AI Powered Smart Support & Ticket Resolution ¦ Start: 18 Feb 2026

## Final Handover
FINAL PROJECT HANDOVER DOCUMENT
Executive Summary | The project achieved its goal of building an AI-powered smart support and ticket resolution system with RAG retrieval, LLM-based response generation, feature expansion across Sprint 5 and Sprint 6, authentication, ticket orchestration, and a planned Streamlit interface for users and administrators.
Velocity Chart (Story Points Completed per Sprint) | Sprint 1: 15, Sprint 2: 12, Sprint 3: 18, Sprint 4: 15, Sprint 5: 15, Sprint 6: 16, Sprint 7: 17, Sprint 8: 18, Sprint 9: 19.
Known Issues / Technical Debt | Potential model latency on CPU-only systems, prompt tuning may still need iterative refinement, and production monitoring/alerting can be strengthened after first live deployment.
Maintenance Guide | To maintain the system: deploy dependencies, ensure Ollama models are available, rebuild the FAISS index when documents change, monitor SQLite database size, and restart the Streamlit app after configuration updates.